## Jayesh
| Task | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
Get Center List | test functionality with postman | 15 mins | 5 mins | Saturday | Complete
| getcenterscomponent.ts | 15mins | 1 hour | Saturday | Error in npm install, took a long time to figure out that the version was wrong
| getcenters.html (Only base UI) | 15 mins | 10 mins | Saturday | Complete
| getcenters() in service | 15 mins | 10 mins | Saturday | Complete
Add Appointment | test functionality with postman | 15minutes | 5 mins | Saturday | complete
| addappointment.ts | 3 hour | 6 hour | Saturday | Pending=>Completed on sunday
| addappointment.html | 1 hour |  | Saturday | Pending=>Completed on sunday
| code for service | 1 hour |  | Sunday | complete
| validation/error handling | 1 hour | 1 hour | Sunday | complete
Approve Appointment | test functionality with postman | 15 minutes | 5 mins | Sunday | complete
| approveappointment.ts | 30 minutes | 1 hour | Sunday | complete
| approveappointment.html | 30 minutes | 30 minutes | Sunday | complete
| code for service | 30 minutes | 30 minutes | Sunday | complete
| validation/error handling | 30 minutes | 30 minutes | Sunday | complete
View Appointment | test functionality with postman | 15 minutes | 10 minutes | Monday | complete
| viewappointment.html\ | 30 minutes | 20 minutes | Monday | complete
| viewappointment.ts | 30 minutes | 30 minutes | Monday | complete
| code for service | 30 minutes | 15 mins | Monday | complete
| validation/error handling | 30 minutes | 5 minutes | Monday | complete
Excel download | Service layer in rest | 30 minutes | 1 hour | Tuesday | complete | had a problem with headers, took time to figure out
| Controller in rest | 30 minutes | 1 hour | Tuesday | complete | had a problem with headers, took time to figure out
| Add button in view appointment | 10 minutes | 10 minutes | Tuesday | complete
| Service in angular | 30 minutes | 1 hour | Tuesday | complete | had a problem with headers, took time to figure out
Java Mailer | research | 1 hour | 30 minutes | Monday | complete
| Implement mailer in approve | 1 hour | 1 hour | Monday | complete | would have finished earlier -> tried to reduce mail sending time... no success
Integrating JWT | Test rest with postman | 1 hour | 2 hour | Monday | complete
| Implement basic hardcoded security for testing | 1 hour | 30 minutes | Tuesday | complete
| login.ts | 30 minutes | 30 minutes | Wednesday | complete
| registration.ts | 30mins | 30 minutes | Wednesday | complete
| error pages . html | 30 mins | 20 minutes | Wednesday | complete
| errorpages.ts | 15 minutes | 15minutes | Wednesday | complete
| basic Auth service | 15 minutes | 15minutes | Wednesday | complete
| login service in angular | 1 hour | 2 hour | Tuesday | Pending=>completed on Wednesday
| register service i nangular | 30 minutes | 30 minutes | Tuesday | Pending=>completed on Wednesday

## Nidhi
| Task | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
Delete Center | test functionality with postman | 15 mins | 15 mins | Saturday | complete
| deletecenter.ts | 1 hour | 1 hour | Saturday | complete
| deletecenter.html | 1 hour | 1 hour | Saturday | complete
| code for service | 1 hour | 1 hour | Saturday | complete
Add test | test functionality with postman | 15 mins | 15 mins | Monday | complete
| addtest.ts | 1 hour | 1 hour | Monday | complete
| addtest.html | 1 hour | 1 hour | Monday | complete
| code for service | 1 hour | 1 hour | Monday | complete
| validation | 2 hours | 2 hour | Monday | complete
Delete Test | test functionality with postman | 15 mins | 15 mins | Tuesday | complete
| deletetest.ts | 2 hours | 2 hours | Tuesday | complete
| deletetest.html | 1 hour | 1 hour | Tuesday | complete
| code for service | 1 hour | 1 hour | Tuesday | complete
Registration | test functionality with postman | 15 mins | 15 mins | Wedneday | complete
| registration.ts | 2 hour | 2 hour | Wedneday | complete
| registration.html | 1 hour | 1 hour | Wedneday | complete
| validation | 2 hour | 2 hour | Wedneday | complete
login | test functionality with postman | 15 mins | 15 mins | Wedneday | complete
| login.ts | 2 hour | 2 hour | Wedneday | complete
| login.html | 30 mins | 30 mins | Wedneday | complete
| validation | 2 hour | 2 hour | Wedneday | complete
Docs | er diagram | 1 hour | 1 hour | Saturday | complete
Designing | Add test | 1 hour | 1 hour | Monday | complete
| delete test | 1 hour | 1 hour | Monday | complete
| add center | 1 hour | 1 hour | Monday | complete

## Kushal
| Task | Estimated hours/Time | Actual Time Taken | Allotted on day
Add Center | test functionality with postman | 15 minutes | 15 minutes | Sunday
| addcenter.ts | 60 minutes | 1 hour | Sunday
| addcenter.html | 30 minutes | 30 minutes | Sunday
| code for service | 30 minutes | 30 minutes | Sunday
| validation/error handling | 30 minutes | 1 hour | Sunday
UI Designing | Reading Templates | 2 hour | 2.5 hour | Monday
| Home page | 2 hour | 2 hour | Monday
| Userhome | 1 hour | 45 minutes | Monday
| AdminHome | 1 hour | 1 hour | Monday
| Implementing more deisgns | 1 hour | 1 hour | Monday
Excel Upload | Controller in Rest | 45 min | 45 min | Tuesday
| Add test html | 20 min | 20 min | Tuesday
| Add test component | 20 min | 20 min | Tuesday
Docs | Activity Diagram | 1 hour | 1 hour | Tuesday
| Sequence Diagram -2 | 1 hour | 1.5 hour | Tuesday
| Wireframe - Home Pages | 1 hour | 1 hour | Tuesday
Designing | Add Center | 2 hour | 3 hour | Wednesday
| Registration | 45 min | 45 min | Wednesday
| Login | 45 min | 45 min | Wednesday
| Error Pages | 30 min | 30 min | Wednesday
| PPT | 1 hour | 1 hour | Wednesday

## Task
Each Task contains the following sub task/module wise work: |  | Main User Story | Sub-Tasks
Test Rest functionality using Postman
code component.ts | 1 | Center | Add Center
code html file of the component (basic UI) |  |  | Remove Center
code service layer
comments in angular | 2 | Test | Add Test
update UI as per the chosen template |  |  | Remove Test
| 3 | Appointment | Add Appointment
Approve Appointment
| 4 | User Miscellaneous | Login
Registration
Logout
View Appointments
Excel Upload
Excel Download
| 5 | Extra work | Email notification on appointment status update